## Project Status & Plan
SAKENI — PROJECT STATUS & IMPLEMENTATION PLAN (MARCH 2025)
1. EXECUTIVE STATUS SUMMARY
Overall Project Health |  | Yellow |  | Entering pre-launch phase. Budget is tight but on track. Focus is on landlord recruitment.
Current Phase |  | Foundation (Phase 1) |  | Building MVP app and securing initial 500 listings.
Budget Status |  | EGP 100K Total |  | EGP 15K spent on Branding/Design. EGP 85K remaining for Dev & Launch.
Timeline Status |  | On Track |  | Targeting MVP launch for Month +6 (September 2025 academic start).
Key Current Risk |  | Supply Cold Start |  | Risk of having too few listings at launch. Mitigating via early landlord outreach.
2. DETAILED IMPLEMENTATION PLAN & STATUS
Task ID | Category | Task Description | Assigned To | Start Date | End Date | % Complete | Status | Cost (EGP) | Notes
T101 | Planning | Market Research & Validation | CEO | M-3 | M-2 | 100% | Complete | 3000 | Surveyed 150 students
T102 | Planning | Business Plan Finalization | CEO | M-2 | M-2 | 100% | Complete | 0 | Completed documents 1-8
T201 | Design | Branding & Logo | Design Lead | M-2 | M-1 | 100% | Complete | 3000 | Figma assets ready
T202 | Design | App UI/UX Wireframes (Figma) | Design Lead | M-1 | M0 | 80% | In Progress | 12000 | Reviewing landlord dashboard
T301 | Tech | Firebase Backend Setup | CTO | M0 | M1 | 20% | In Progress | 5000 | Configuring Auth & Firestore
T302 | Tech | Flutter App - Student Core | CTO | M1 | M3 | 0% | Not Started | 25000 | Await final Figma screens
T303 | Tech | Flutter App - Owner Core | CTO | M2 | M4 | 0% | Not Started | 20000 | Includes Listing management
T304 | Tech | In-App Chat Module | CTO | M3 | M4 | 0% | Not Started | 5000 | Critical MVP feature
T401 | Operations | Landlord Pre-Recruitment | Sales | M1 | M5 | 10% | In Progress | 5000 | Target: 500 listings
T402 | Legal | Company Registration | CEO | M2 | M3 | 0% | Not Started | 5000 | Establish LLC in Egypt
T501 | Marketing | App Store Setup & ASO | Mktg | M4 | M5 | 0% | Not Started | 5000 | Google Play + Apple Dev accounts
T502 | Marketing | Digital Launch Campaign | Mktg | M5 | M6+ | 0% | Not Started | 10000 | Facebook + TikTok Ads
TOTAL ESTIMATED MVP BUDGET: | [7 empty] | 98000 | Remaining contingency: EGP 2,000 (of 100K Total)