## Product Roadmap
SAKENI — Product Development Roadmap ¦ March 2025 – 2028
Student Housing & Real Estate Platform — Egypt
LEGEND: |  | Phase 1: Launch (0-6 mo) |  |  | Phase 2: Scale (6-18 mo) |  |  | Phase 3: Expand (2-4 yr) |  |  | Completed | In Progress
Feature / Milestone |  | M1-2 | M3-4 | M5-6 | M7-9 | M10-12 | Q5-6 | Q7-8 | Y3 | Y4 | Ongoing
PHASE |  | PHASE 1: LAUNCH | [5 empty] | PHASE 2: SCALE |  | PHASE 3: EXPAND
PHASE 1 FOUNDATION | Market Research & Validation | █ | ✓
| Branding & Logo Design | █ | ✓
| UI/UX Design (Figma) | █ | █ | ✓
| Flutter App Development |  | █ | █ | █
| Firebase Backend Setup |  | █ | █
| Landlord Pre-Recruitment | █ | █ | █
| Beta Testing (100 users) |  |  | █ | █
| App Store Launch |  |  |  | █
| Initial Marketing Campaign |  |  |  | █ | █
| Reach 5,000-8,000 Students |  |  |  |  | █
| Reach 500-700 Listings |  |  |  |  | █
PHASE 2 GROWTH | Payment Gateway Integration | [5 empty] | █ | █
| Escrow Security Deposit System | [6 empty] | █
| Advanced Rating & Reviews | [5 empty] | █ | █
| Expand to More Cairo Univeristies | [5 empty] | █ | █
| Reach 50,000 Students | [6 empty] | █
| Reach 5,000 Listings | [6 empty] | █
| Achieve Revenue Break-Even | [6 empty] | █
PHASE 3 EXPAND | Provincial Cities Expansion | [7 empty] | █ | █
| Property Buy/Sell Marketplace | [7 empty] | █ | █
| AI-Powered Matching Engine | [8 empty] | █
| Digital Lease Contracts | [7 empty] | █
| Agency & B2B Portal | [8 empty] | █
| Series A Funding Round | [7 empty] | █
| 200,000+ Active Users | [8 empty] | █
ONGOING | Customer Support & Feedback |  |  | █ | █ | █ | █ | █ | █ | █ | █
| Security & Bug Fixes |  |  |  | █ | █ | █ | █ | █ | █ | █
| Content Marketing & SEO |  | █ | █ | █ | █ | █ | █ | █ | █ | █

## Milestones & KPIs
SAKENI — Key Milestones & Success KPIs
PHASE 1: LAUNCH (Months 1-6)
Milestone | Target Date | Success Metric | Quality Indicator | Phase | Owner | Status
App Goes Live on Google Play & App Store | Month 5 | 500 downloads in Week 1 | App Store listing live | Phase 1 | Sakeni Team | Planned
First 100 Verified Listings | Month 3 | 100 landlords registered & verified | Listing quality > 4.0 stars | Phase 1 | Sakeni Team | Planned
First 1,000 Registered Students | Month 5 | 1,000 accounts created | DAU/MAU ratio > 25% | Phase 1 | Sakeni Team | Planned
First 5,000-8,000 Students (End of Phase 1) | Month 6 | 8,000 registered students | Monthly chat messages > 10,000 | Phase 1 | Sakeni Team | Planned
500-700 Active Listings | Month 6 | 700 verified listings | Avg listing view rate > 15/week | Phase 1 | Sakeni Team | Planned
First Paying Landlords (50+) | Month 5-6 | EGP 5,000-7,500 MRR | Churn rate < 10% | Phase 1 | Sakeni Team | Planned
PHASE 2: SCALE (Months 7-18)
Milestone | Target Date | Success Metric | Quality Indicator | Phase | Owner | Status
Payment Gateway Live | Month 9 | 50 security deposit transactions | Zero payment failures | Phase 2 | Sakeni Team | Planned
Expand to 5 Additional Universities | Month 12 | 5 new campus zones | New listings per zone > 200 | Phase 2 | Sakeni Team | Planned
50,000 Registered Students | Month 15-18 | 50K registered users | NPS score > 50 | Phase 2 | Sakeni Team | Planned
5,000 Active Listings | Month 18 | 5,000 verified listings | Avg landlord rating > 4.2 | Phase 2 | Sakeni Team | Planned
Revenue Break-Even | Month 10-12 | MRR > EGP 8,000/month | Gross margin > 70% | Phase 2 | Sakeni Team | Planned
Series Seed Funding | Month 12-18 | EGP 500K-1M raised | Runway > 24 months | Phase 2 | Sakeni Team | Planned
PHASE 3: EXPAND (Years 2-4)
Milestone | Target Date | Success Metric | Quality Indicator | Phase | Owner | Status
Provincial Expansion (Alexandria, Mansoura, Assiut) | Year 3 | 3 cities live | 50K listings nationwide | Phase 3 | Sakeni Team | Planned
Real Estate Buy/Sell Marketplace | Year 3 | 1,000 property sale listings | EGP 5M+ in commissions/year | Phase 3 | Sakeni Team | Planned
200,000 Active Users | Year 3-4 | 200K MAU | Retention > 60% annually | Phase 3 | Sakeni Team | Planned
Series A Funding | Year 3 | EGP 5M-15M raised | MENA expansion readiness | Phase 3 | Sakeni Team | Planned
EGP 10M+ Annual Revenue | Year 3-4 | EGP 10M ARR | Net margin > 30% | Phase 3 | Sakeni Team | Planned